## "Your Project" "Role" Schedule
"Your Project" "Role" Schedule |  | Report
Starting Date | 2001-10-10 | Est Finish Date |  |  | 2001-10-12 19:12
Delivery Date | 2002-10-10 | Projected Finish Date |  |  | 2076-03-07
Hrs per day | 7.5 | Average Hrs per day |  |  | 0.00077271
Days per week | 5 | Average Hrs per week |  |  | 0.0038636
Feature | Task | Priority | Orig Est | Curr Est | Elapsed | Remain
Feature 1 | Task 1 |  | 4 | 3 | 3
| Task 2 | 1 | 6 | 8 | 2 | 6
| Task 3 | 2 | 4 | 4 |  | 4
Total Hrs |  |  | 14 | 15 | 5 | 10
Total Days |  |  | 1.8667 | 2 | 0.66667 | 1.3333
Total Weeks |  |  | 0.37333 | 0.4 | 0.13333 | 0.26667
Finish Dates |  |  | 2001-10-12 14:43 | 2001-10-12 19:12 |  | 2026-07-31 20:48
The aim of this exercise is to break each feature down to tasks of less than 8 hours each. If you have a task that is over 8 hours then the likelyhood is that it can be broken down further.
1. Replace "Your Project" with the name of the project, and replace "Role" with your role within the project Note: Role is unecessary if you're the only person working on the project
2. Put your initial hourly estimates into the "Orig Est" column and copy into the "Curr Est" column. The "Orig Est" column shouldn't be changed from this point unless you add to the task list.
3. Make sure you update the "Curr Est" and "Elapsed" columns as you do the work
4. Make sure you add to the Task list if you work on something not already on the list, otherwise your average hours will reflect less than they should.
5. Sometimes your Original Estimate will be less than your Current (or actual) Estimate, other times it will be more. If a pattern emerges between the "Orig Est" and "Curr Est" columns then keep that in mind for next time.
6. Don't "massage" your times to make the Average Hrs look better. If your Average Hrs don't accurately reflect your Hrs per day it's ok, it doesn't you're slacking off, it just means you need to assess the situation and improve on it either by reducing the expected hours, reducing distractions, or including other activities.
7. To add more rows, insert the number of rows needed and copy or "fill down" existing rows so the formulas follow through.